## Tasks
Ordinal Number | Task | Content | Coder | Star Date | End Date | Doing Time | Status
1 | Merge Admin Layout | Split and convert the admin template's content from HTML into the project | Ngo Hoang Phuc | 2020-08-12 | 2020-09-12 | 1 days | Done
2 | CRUD Category functions | Admin can create a new category for products | Ngo Hoang Phuc | 2020-09-12 | 2020-09-12 | 2 hours | Done
3 | Login and Log out Admin | Admin needs to log them in in oder to access to the site | Ngo Hoang Phuc | 20/12/2020 | 21/12/2020 | 1 day | Done
4 | CRUD Brand | Admin can create a new brand | Ngo Hoang Phuc | 2020-12-12 | 2020-12-12 | 2 hours | Done
5 | Search function for All Table | Search for brand, category, item and invoice | Ngo Hoang Phuc | 15/12/2020 | 29/12/2020 | 14 days | Done
6 | Read Vendors and Customer information | Admin can see a list of customer and vendor accounts | Ngo Hoang Phuc | 2020-11-12 | 2020-11-12 | 3 hours | Done
7 | Read Product Ratings table | Admin can see product rating status | Ngo Hoang Phuc | 25/12/2020 | 25/12/2020 | 1 hours | Done
8 | Read statistics in the current month |  | Ngo Hoang Phuc | 27/12/2020 | 27/12/2020 | 1 hours | Done
9 | block or unblock accounts, delete accounts | Admin has the right to manage the accounts of the staff, customer, and the admin can block the fraudulent users. | Ngo Hoang Phuc | 13/12/2020 | 14/12/2020 | 1 days | Done
10 | Read Order History | Admin can see a list of invoices made in a month, year | Ngo Hoang Phuc | 25/12/2020 | 25/12/2020 | 1 hours | Done
11 | Read And Delete Product | Admin can delete illegal products | Ngo Hoang Phuc | 2020-10-12 | 15/12/2020 | 5 days | Done
12 | Warning low rated-products | Send warning email to vendor if the product is rated low stars | Ngo Hoang Phuc | 25/12/2020 | 26/12/2020 | 1 days | Done
1 | Analyse and design Database | Design database pattern | Nguyen Hong Son | 2020-08-12 | 2020-12-12 | 4 days | Done
2 | Security | Security system | Nguyen Hong Son | 13/12/2020 | 16/12/2020 | 3 days | Done
3 | Sign Up and Login, update profile Vendor | Vendor needs to have a account to sell their product | Nguyen Hong Son | 17/12/2020 | 19/12/2020 | 3 days | Done
4 | CRUD functions for Product | Vendor can create and update, remove their products' information | Nguyen Hong Son | 20/12/2020 | 22/12/2020 | 3 days | Done
5 | Read and Update Order New | View new orders, view details and send mail and update order status | Nguyen Hong Son | 23/12/2020 | 25/12/2020 | 3 days | Done
6 | Send respone Email to Customer | send mail to the customer to confirm the order has been approved for the customer and transport status | Nguyen Hong Son | 25/12/2020 | 26/12/2020 | 2 days | Done
7 | Read history order, see detail | Vendor can see the order of their shop that made in the past | Nguyen Hong Son | 26/12/2020 | 28/12/2020 | 2 days | Done
8 | Read rate quality of product | See the total for each star category of a product rated by the customer, for quality thanks to the general column of the table | Nguyen Hong Son | 29/12/2020 | 30/12/2020 | 2 days | Done
9 | Search functions | Search for product, order new, history order, rate | Nguyen Hong Son | 31/12/2020 | 2020-02-01 | 3 days | Done
10 | statistic | Dashboard of sold product, total order by date, draw the chart | Nguyen Hong Son | 2021-03-01 | 2021-01-04 | 2 days | Done
11 | Fix bug | Fix some errors for all features | Nguyen Hong Son | 2021-05-01 | 2021-01-05 | 6 hours | Done
1 | Merge Client Layout | Split and convert the store template's content from HTML into the project | Nguyen Phuong Minh Thong | 2020-08-12 | 2021-06-01 | 28 days | Done
2 | Latest and Special and Related Products | A page of discounted, special items | Nguyen Phuong Minh Thong | 2020-12-12 | 2020-12-12 | 1 day | Done
3 | Login and Sign Up Customer | Customer needs to log them in in oder to access to the store | Nguyen Phuong Minh Thong | 12/13/2020 | 12/21/2020 | 8 days | Done
4 | Create and Delete Order Invoice | Customer can choose to cancel the delivery after making a purchase | Nguyen Phuong Minh Thong | 12/19/2020 | 12/22/2020 | 3 days | Done
5 | Invoice History | The customer can access to the orders history to see their previous invoice | Nguyen Phuong Minh Thong | 12/19/2021 | 12/20/2021 | 1 day | Done
6 | Shopping Cart | Customer can add item into cart for later purchase | Nguyen Phuong Minh Thong | 2020-12-12 | 12/16/2020 | 4 days | Done
7 | Purchase Function | After choosing products to buy, the customer need to fill in the delivery form | Nguyen Phuong Minh Thong | 12/16/2020 | 12/20/2020 | 4 days | Done
8 | Paypal purchase | Online payment method for customer | Nguyen Phuong Minh Thong | 12/16/2020 | 2021-06-01 | 25 days | Undone
9 | CRUD Customer functions | Necessary functions for customer site | Nguyen Phuong Minh Thong | 12/13/2020 | 12/23/2020 | 10 days | Done
10 | Profile Customer | A site for customer to see and update their personal information | Nguyen Phuong Minh Thong | 12/23/2020 | 2021-01-01 | 8 days | Done
11 | Search function for Product name and Vendor name | Customer can search for item by typing name of the item or name of the vendor | Nguyen Phuong Minh Thong | 2020-12-12 | 12/31/2020 | 19 day | Done
12 | ForgetPassword | An email will sent to the customer email address leads to the resetpassword page | Nguyen Phuong Minh Thong | 12/28/2020 | 12/31/2020 | 3 days | Done
13 | List of Products on main page | Display product on main page | Nguyen Phuong Minh Thong | 2020-12-12 | 12/19/2020 | 7 days | Done
14 | List of Categories on the main page | Display a list of inserted categories on the side bar of the page | Nguyen Phuong Minh Thong | 12/13/2020 | 12/13/2020 | 2 hours | Done
15 | Product pagination | Limited number of products displayed for each page | Nguyen Phuong Minh Thong | 12/13/2020 | 12/20/2020 | 7 days | Done
16 | Product Listed by Brands | Display products owned by brand's id | Nguyen Phuong Minh Thong | 12/18/2020 | 12/19/2020 | 1 day | Done
17 | Email for customer | Send a confirm email to customer after they made a purchase, or when the customer deactivate their accounts | Nguyen Phuong Minh Thong | 12/21/2020 | 12/22/2020 | 1 day | Done
18 | Product Detail | Display product's homw page for more information | Nguyen Phuong Minh Thong | 12/21/2020 | 12/25/2020 | 4 days | Done
19 | Rating Feature | Rating system for product's quality | Nguyen Phuong Minh Thong | 12/21/2020 | 2021-06-01 | 16 days | In progress
Nguyen Phuong Minh Thong
Reporter | Nguyen Hong Son | 2021-06-01
Ngo Hoang Phuc